## Sayfa1
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
TASK | START | END | DAYS | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F
Collaborating group | 2019-09-23 | 2019-10-07 | 15
Deciding project topic | 2019-10-08 | 2019-10-08 | 1
Deciding project tools | 2019-10-09 | 2019-10-13 | 5
Gathering RAD | 2019-10-14 | 2019-11-10 | 27
Implementation | 2019-10-28 | 2020-01-17 | 85
Update RAD | 2019-11-11 | 2019-11-17 | 7
Database | 2019-11-18 | 2019-11-27 | 10
Software Architecture | 2019-11-28 | 2019-12-08 | 11
Boundary Conditions | 2019-12-09 | 2019-12-13 | 5
Gathering SDD&Updates | 2019-12-14 | 2019-12-15 | 2
Gathering ODD&Updates&Beta Test | 2019-12-16 | 2019-12-22 | 7
Full Test | 2019-12-23 | 2020-01-17 | 30

## Sayfa2
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
WBS | TASK | START | END | DAYS | M | T | W | Th | F | S | Su | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Analyze requirements
Design
Redesign existing compenents
Design new compenents
Design interfaces
Implement
Implement new code
Modify existing code
Finish implementation
Develop integration plan
Finish unit testing
update documentation
integrate and test
develop integration tests
perform integration tests
perform acceptence tests